## Foglio1
Macro-phase | Phase | Sub-phase | Deliverables | Responsibile Roles | Accountable Roles | Timing | Suggested Date
Kick Off project | Kick Off project | Target finalization
Kick Off project | Kick Off project | Lesson learned
Project planning (by module) | Project planning (by module) | Project planning (by module)
Project planning (by module) | Project planning (by module) | Modules validation
Planning | module definition | Modules priorities and cost allocation
Existing solution adaptation | existing solution adaptation | Cross-check within company, group and market
New solutions design | Ideas Generation | Specs, needs and expectations review
New solutions design | Ideas Generation | Components specification
New solutions design | Ideas Generation | AT&I specification
New solutions design | Ideas Generation | Modul strategy analysis: make, buy or co-design
New solutions design | Ideas Generation | Internal & external Design review
New solutions design | Machine design | Project pillars design
New solutions design | Machine design | Design for standardization
New solutions design | Machine design | Technical supervision based on costs control
New solutions design | Machine design | FMEA Analysis
New solutions design | Machine design | Machine new Bricks creations
New solutions design | Machine design | Common glossary definition and standardization
New solutions design | Machine design | Actual cost real time update and DFX checks
New solutions design | Size parts design | Size parts prioritization
New solutions design | Size parts design | Rough analysys of specs sentivity
New solutions design | Digital features design (Kinematic Analysis) | Features/Parameters definition
New solutions design | Digital features design (Kinematic Analysis) | Process optimization
New solutions design | Pneumatic, vacuum hydraulic and electrical system design | Guidleline definition
New solutions design | Pneumatic, vacuum hydraulic and electrical system design | Assembly phase optimization
New solutions design | HW devices and cabinet design | Wiring and Testing phase optimization
New solutions design | SW design | Cross-check within company and group
New solutions design | SW design | Testing phase optimization
New solutions design | SW design | HMI internal users experience definition
New solutions design | Layout design | Standard layout definition
New solutions design | Lift & Movements design | Standard jigs definition and re-use
Industrialization & cost optimization | Post design activities | S&OP simulation
Industrialization & cost optimization | Post design activities | Material Strategy definition
Industrialization & cost optimization | Post design activities | Sequencing (rough hypothesis)
Industrialization & cost optimization | Post design activities | Components risk assesment
Industrialization & cost optimization | Post design activities | Cost analysis and Preliminary DTC action to be planned
Industrialization & cost optimization | Post design activities | Final design review
Simulation/Proof of principle/Module prototyping/back-up solution | Simulation/Proof of principle/Module prototyping/back-up solution | Machine ergonomics analysis
Virtual commissioning and module design review | Virtual commissioning and module design review | Machine verification and stress for optimization
System integration and verification | System integration and verification | Change Request management
System integration and verification | System integration and verification | Structured Team Retrospective
Documentation & Processes | Documentation & Processes | Documentation AT&I
Documentation & Processes | Documentation & Processes | Operation process design
Documentation & Processes | Documentation & Processes | Digital service AT&I Design
Documentation & Processes | Documentation & Processes | New industrialization initiative design
Preliminary BOM (engineering, assembly and services) | Preliminary BOM (engineering, assembly and services) | Ebom creation
Preliminary BOM (engineering, assembly and services) | Preliminary BOM (engineering, assembly and services) | Mbom simulation + Sequencing
Manufacturing | BOM analysis with SC perspective | Detailed material strategy definition
Manufacturing | BOM analysis with SC perspective | Outsourcing vs insourcing
Manufacturing | Drawing components purchasing | Supplier detailed agreement and strategy
Manufacturing | Commercial components purchasing | Supplier detailed agreement and strategy
Manufacturing | Schedule Agreement purchasing | Supplier detailed agreement and strategy
Manufacturing | External pre-Assemblies purchasing | Supplier detailed agreement and strategy
Manufacturing | Co - Designed groups purchasing | Supplier detailed agreement and strategy
Manufacturing | Cabinet purchasing | Supplier detailed agreement and strategy
Manufacturing | SC management | Supply chain quality and Risk assessment
Manufacturing | Quality checks for components and group | Quality defect database creation
Manufacturing | Inventory management and simulation | Inventory management and simulation
Manufacturing | Materials handling | Assembly cells balancing
Assembly | Groups assembly (stand-alone) | Top 5 losses & cost update
Assembly | Groups assembly (stand-alone) | Assembly centerline creation
Assembly | Groups assembly (stand-alone) | Top 5 quality issues (design components)
Assembly | Modules stan-alone assembly/wiring and final installation on framework | Sequence validation and line balancing update
Assembly | Modules stan-alone assembly/wiring and final installation on framework | Top 5 losses & cost update
Assembly | Cabinet testing | Top 5 losses & cost update
Assembly | Cabinet testing | Testing protocol and testing tools definition
Assembly | Machine completion (modules and wiring) | Top 5 losses & cost update
Assembly | Machine completion (modules and wiring) | Assembly centerline creation
Assembly | Machine completion (modules and wiring) | Maintaining operations evaluation
Assembly | Machine guards installation | Safety visual check
Assembly | Machine transport to testing areas | Top 3 losses (JIG application/removal)
Testing and acceptance | Machines and layout placement and connection | Installation and sequence analisys and optimization
Testing and acceptance | Machines and layout placement and connection | Top 5 losses & cost update
Testing and acceptance | Power on & dry run | Machine standard adjustment and testing protocol definition
Testing and acceptance | Power on & dry run | Sequential testing hypothesis definition
Testing and acceptance | Power on & dry run | Top 5 losses & cost update
Testing and acceptance | Power on & dry run | Dry run centerline creation
Testing and acceptance | Materials unwinding | Parameters list and centerline definition/completion
Testing and acceptance | Materials unwinding | Top 5 losses & cost update
Testing and acceptance | Wrapping tests | Parameters list and centerline definition/completion
Testing and acceptance | Wrapping tests | Top 5 losses & cost update
Testing and acceptance | Final quality checks, PreFAT and FAT | HMI analysis & feedback
Testing and acceptance | Final quality checks, PreFAT and FAT | Testing centerline creation
Testing and acceptance | Final quality checks, PreFAT and FAT | Product quality report
Testing and acceptance | Final quality checks, PreFAT and FAT | Machine status
Testing and acceptance | Disconnection and Shipment | Top 5 losses & cost update
Testing and acceptance | Disconnection and Shipment | Shipment centerline creation
Final design definition | Final design definition | Final design review and cost update
Final design definition | Change request analysis | Change requests filter and prioritization
Final BOM (engineering,assembly and sevices) | Final BOM (engineering,assembly and sevices) | Ebom completion
Installation & SAT - Market launch | Installation | Top 5 installation losses
Installation & SAT - Market launch | Commissioning | Troubleshooting database creation
Installation & SAT - Market launch | SAT | Product quality report and wrapping material specification
Installation & SAT - Market launch | SAT | Machine digital identity card creation
Final BOM (engineering,assembly and sevices) | Final BOM (engineering,assembly and sevices) | Mbom/Sbom creation and sequencing update
Handover | Project retrospective | Structured Team Retrospective

## Foglio2
Role | Name | Email
Head of Project Controlling | Martina Mondelli | martina.mondelli@gfe.it
Head of Engineering | Mattia Meccagni | mattia.meccagni@gidi.it
Industrialization Manager | Filippo Menichelli | filippo.menichelli@emmeci.it
Operations Project Leader | Cristian Rossi | cristian.rossi@gidi.it
Product Owner | Simone Frontini | simone.frontini@systemceramics.com
Head of Project Management | Carlos Garcia Fernandez | carlos.garciaf@volpak.com
Assembly Project Leader | Daniele Grosso | daniele.grosso@gidi.it
Testing Project Leader | Giada Magherini | giad.magherini@gidi.it
Installation Project Leader | Marco Pavesi | marco.pavesi@gidi.it